## Scope
Whatsapp Group - Client Scope
# | Task List | Response
1 | There will be a front end to register and buy plans which would be monthly rental plans that can be bought monthly or annually from the frontend
2 | Razor pay payment gateway will be integrated and we will provide the details for the same. |  | Not Feasible
3 | Payment plans will be depending on number of whatsapp numbers to be used as well as number of groups to be created |  | Need Clarification (Discussion)
4 | Admin panel will be there who can manage everything for the system, admin can create users, admin can also create users from the backend and attach plans to them.
5 | Admin can create or remove plans, change descriptions of plan, pointers to compare the plans, Increase or decrease price plans, admin can fix monthly as well as annual plans in the backend
6 | User would be able to login using email id and mobile number
7 | Users would be able to scan the whatsapp number, set profile name, set profile image if possible | Personal Whatsapp Used for this
8 | Users would be able to create a group, set group name, set group image and title should follow the same limit which whatsapp have that means text limit
9 | Users would be able to upload csv or excel in format first name, last name and mobile number to the system and the same will be added to the group. Users would be able to manually add or remove any user from the group
10 | User would be able to send message as text only, text + image, image only, video only, video + image to the group
11 | Users would be able to design templates also to send to the users with features like bold text, add link to the text
12 | Users would be able to schedule the messages in advance as when and at what time messages should go to the group, while scheduling users would be able to select the group also to which message should be posted
13 | If user will start to create more group as per the plan limit than user would be asked to upgrade to the plan before proceeding forward, as soon as it gets upgraded than limit will increase
14 | Users would be able to read and reply to messages from the panel and also would be able to do personal chats to users to accept orders as well as communicate and update. | Chat Application like send / Receive Messages
15 | Admin dashboard will have all analytics like number of users, number of groups, number of messages sent, number of messages received, revenue earned with graphs and can be further breakdown or filters as per date and time filter

## Web Application
Tasklist for Whatsapp Group - Web Application
# | Module | Sub Module | Task List | Timeline in Hours | Expected Start Date | Expected End Date
1 | Database | Database Creation | Database and Table Structure Define and Creation. | 6 | 2023-10-03 | 2023-10-03
2 | Website Template | Website Template | Website Template customization | 4 | 2023-10-03 | 2023-10-03
3 | Login | User Login | Mobile No or Email | 1 | 2023-10-04 | 2023-10-04
4 |  |  | Password
5 |  |  | Login Button
6 | Register | User Register | Get User Name, Email & Mobile No | 2 | 2023-10-04 | 2023-10-04
7 |  |  | Get OTP and validate with Mobile No
8 |  |  | Password and Confirm Password
9 |  |  | Register Button
10 | Forgot Password | Forgot Password | Mobile No with OTP and Password | 1 | 2023-10-04 | 2023-10-04
11 | User Dashboard | Header Panel | Allowed Numbers of Whatsapp and Group Count and Balance | 1 | 2023-10-04 | 2023-10-04
12 |  | Change Password | Change Password | 2 | 2023-10-27 | 2023-10-27
13 |  | User Profile | User Profile View | 4 | 2023-10-30 | 2023-10-30
14 |  |  | User Profile Update
15 |  | Dashboard | Summary Report of Created Group | 6 | 2023-10-27 | 2023-10-27
16 |  |  | Summary Report of No of Message Sent
17 |  |  | Summary Report of No of Message Received
18 |  |  | Graph for Message send / Receive
19 | Plans | Show Plans | Show Monthly / Annual Plans with description | 1 | 2023-10-04 | 2023-10-04
20 |  |  | Compare Plans | 4 | 2023-10-05 | 2023-10-05
21 |  |  | Payment via Razorpay | 4 | 2023-10-05 | 2023-10-05
22 |  |  | Show Purchased Plans with description | 1 | 2023-10-06 | 2023-10-06
23 |  |  | Order History | 1 | 2023-10-06 | 2023-10-06
24 |  |  | All Purchased History | 2 | 2023-10-06 | 2023-10-06
25 |  |  | Renew Plans | 4 | 2023-10-06 | 2023-10-06
26 | Sender ID | Sender ID Creation | Scan Whatsapp No with Country Code | 2 | 2023-10-09 | 2023-10-09
27 |  |  | Set Profile Name, Image | 4 | 2023-10-09 | 2023-10-09
28 |  |  | Add Title | 2 | 2023-10-09 | 2023-10-09
29 |  |  | Create Sender ID
30 |  | Sender ID List | Show All Sender ID | 1 | 2023-10-10 | 2023-10-10
31 |  |  | Edit / Delete the Sender ID | 3 | 2023-10-30 | 2023-10-30
32 |  |  | Search Filters for Sender ID List
33 |  |  | Export the Sender ID List
34 | Group | Add Group | Add Group Title | 1 | 2023-10-10 | 2023-10-10
35 |  |  | Import Mobile numbers, First Name, Last Name with CSV/Excel
36 |  |  | Manually Add / Modify Users in the Group | 4 | 2023-10-10 | 2023-10-10
37 |  |  | Manually Remove Users in the Group | 2 | 2023-10-10 | 2023-10-10
38 |  |  | Check the Group list. If exceeds the limit show Upgrade plan | 6 | 2023-10-11 | 2023-10-11
39 |  | Group List | Show All Groups | 1 | 2023-10-11 | 2023-10-11
40 |  |  | Edit / Delete the Group | 3 | 2023-10-31 | 2023-10-31
41 |  |  | Search Filters for Group List
42 |  |  | Export the Group List
43 | Template | Create Template | Create Message Template with Name and Message | 8 | 2023-10-12 | 2023-10-12
44 |  |  | Bold, Add Link in the Message Template
45 | Message | Compose Message | Compose Message with Only Text | 2 | 2023-10-13 | 2023-10-13
46 |  |  | Compose Message with Only Image | 2 | 2023-11-01 | 2023-11-01
47 |  |  | Compose Message with Only Video | 2 | 2023-11-01 | 2023-11-01
48 |  |  | Compose Message with Text + Image | 2 | 2023-11-01 | 2023-11-01
49 |  |  | Compose Message with Video + Image | 4 | 2023-11-01 | 2023-11-01
50 |  |  | Choose Template | 2 | 2023-10-13 | 2023-10-13
51 |  |  | Choose Group
52 |  |  | Choose Schedule Message time or Now Send
53 |  |  | Send Message
54 |  | Messages List | Show All Messages | 1 | 2023-10-13 | 2023-10-13
55 |  |  | Search Filters for Messages List | 3 | 2023-11-02 | 2023-11-02
56 |  |  | Export the Messages List
57 | Chat | Chat | Send / Receive Chat Messages | 6 | 2023-11-02 | 2023-11-02
58 | Admin Panel | Dashboard | Summary Report of No of Users with Graph | 24 | 2023-11-07 | 2023-11-09
59 |  |  | Summary Report of No of Groups with Graph
60 |  |  | Summary Report of No of Messages Sent with Graph
61 |  |  | Summary Report of No of Messages Received with Graph
62 |  |  | Summary Report of No of Revenue Earned with Graph
63 |  | User Creation | Get user details including Name, Email and Password | 4 | 2023-10-16 | 2023-10-16
64 |  |  | Get OTP for validate the Mobile No
65 |  |  | Assign Plans
66 |  |  | Create User
67 |  | User List | Show All users with Plans | 1 | 2023-10-13 | 2023-10-13
68 |  |  | Edit / Delete the User | 3 | 2023-11-03 | 2023-11-03
69 |  |  | Search Filters for User List
70 |  |  | Export the User List
71 |  | Plan Creation | New Plan Title | 4 | 2023-10-16 | 2023-10-16
72 |  |  | Monthly / Annual Price
73 |  |  | No of Whatsapp and Groups created
74 |  |  | Create Plan
75 |  | Plan List | Show All Existing Plans | 2 | 2023-10-17 | 2023-10-17
76 |  |  | Monthly / Annual Plans with Cost
77 |  |  | Add / Edit / Delete the Plans | 6 | 2023-10-17 | 2023-10-17
78 |  |  | Search Filters for Plan List
79 |  |  | Export the Plan List
80 |  | Report Management | Details Report of No of Users | 2 | 2023-11-03 | 2023-11-03
81 |  |  | Details Report of No of Groups | 2 | 2023-11-03 | 2023-11-03
82 |  |  | Details Report of No of Messages Sent | 2 | 2023-11-03 | 2023-11-03
83 |  |  | Details Report of No of Messages Received | 2 | 2023-11-06 | 2023-11-06
84 |  |  | Details Report of No of Revenue Earned | 2 | 2023-11-06 | 2023-11-06
85 |  |  | Search Filters for All reports | 2 | 2023-11-06 | 2023-11-06
86 |  |  | Export the All reports | 1 | 2023-11-06 | 2023-11-06
87 | Testing | Internal Testing and Issue Fixing | Round 1 - Testing | 8 | 2023-10-18 | 2023-10-18
88 |  |  | Issue Fixing | 12 | 2023-10-19 | 2023-10-20
89 |  |  | Round 2 - Testing | 8 | 2023-10-20 | 2023-10-25
90 |  |  | Issue Fixing | 8 | 2023-10-25 | 2023-10-26
91 |  |  | Round 3 - Testing | 4 | 2023-10-26 | 2023-10-27
92 |  | User Acceptance Testing (UAT) and Issue Fixing | Round 1 - Testing | 8 | 2023-11-10 | 2023-11-10
93 |  |  | Issue Fixing | 12 | 2023-11-13 | 2023-11-14
94 |  |  | Round 2 - Testing | 8 | 2023-11-14 | 2023-11-15
95 |  |  | Issue Fixing | 8 | 2023-11-15 | 2023-11-16
96 |  |  | Round 3 - Testing | 4 | 2023-11-16 | 2023-11-16
Total : |  |  |  | 222
| Required Details | OTP API required |  |  | Phase I
|  | SMTP & EMail login details required |  |  | Phase II
Razor Pay Payment & login details required (Staging Test / Live)

## Completed Tasks
Completed Tasklist for Whatsapp Group
# | Module | Sub Module | Task List | Status | Timeline in Hours | Expected Start Date | Expected End Date
1 | Database | Database Creation | Database and Table Structure Define and Creation. | Completed | 6 | 2023-10-03 | 2023-10-03
2 | Website Template | Website Template | Website Template customization | Completed | 4 | 2023-10-03 | 2023-10-03
3 | Login | User Login | Mobile No or Email | Completed | 1 | 2023-10-04 | 2023-10-04
4 |  |  | Password | Completed
5 |  |  | Login Button | Completed
6 | Register | User Register | Get User Name, Email & Mobile No | Completed | 2 | 2023-10-04 | 2023-10-04
7 |  |  | Get OTP and validate with Mobile No | Pending
8 |  |  | Password and Confirm Password | Completed
9 |  |  | Register Button | Completed
10 | Forgot Password | Forgot Password | Mobile No with OTP and Password | Completed & Issue | 1 | 2023-10-04 | 2023-10-04
11 | User Dashboard | Header Panel | Allowed Numbers of Whatsapp and Group Count and Balance | Completed & Issue | 1 | 2023-10-04 | 2023-10-04
12 |  | Change Password | Change Password | Phase - II | 2
13 |  | User Profile | User Profile View | Phase - II | 4
14 |  |  | User Profile Update | Phase - II
15 |  | Dashboard | Summary Report of Created Group | Phase - II | 6
16 |  |  | Summary Report of No of Message Sent | Phase - II
17 |  |  | Summary Report of No of Message Received | Phase - II
18 |  |  | Graph for Message send / Receive | Phase - II
19 | Plans | Show Plans | Show Monthly / Annual Plans with description | Completed | 1
20 |  |  | Compare Plans | Completed | 4
21 |  |  | Payment via Razorpay | Completed | 4
22 |  |  | Show Purchased Plans with description | Completed | 1
23 |  |  | Order History | Completed | 1
24 |  |  | All Purchased History | Completed | 2
25 |  |  | Renew Plans | Completed | 4
26 | Sender ID | Sender ID Creation | Scan Whatsapp No with Country Code | Completed | 2
27 |  |  | Set Profile Name, Image | Completed | 4
28 |  |  | Add Title | Completed | 2
29 |  |  | Create Sender ID | Completed
30 |  | Sender ID List | Show All Sender ID | Completed | 1
31 |  |  | Edit / Delete the Sender ID | Phase - II | 3
32 |  |  | Search Filters for Sender ID List | Phase - II
33 |  |  | Export the Sender ID List | Phase - II
34 | Group | Add Group | Add Group Title | Completed | 1
35 |  |  | Import Mobile numbers, First Name, Last Name with CSV/Excel | Completed
36 |  |  | Manually Add / Modify Users in the Group | Completed | 4
37 |  |  | Manually Remove Users in the Group | Completed | 6 | 2024-01-12 | 2024-01-17
38 |  |  | Check the Group list. If exceeds the limit show Upgrade plan | Completed | 2 | 2024-01-13 | 2024-01-17
39 |  | Group List | Show All Groups | Completed | 1
40 |  |  | Edit / Delete the Group | Phase - II | 3
41 |  |  | Search Filters for Group List | Phase - II
42 |  |  | Export the Group List | Phase - II
43 | Template | Create Template | Create Message Template with Name and Message | Completed | 8 | 2024-01-17 | 2024-01-22
44 |  |  | Bold, Add Link in the Message Template | Completed
45 | Message | Compose Message | Compose Message with Only Text | Completed | 2 | 2024-01-18 | 2024-01-18
46 |  |  | Compose Message with Only Image | Phase - II | 2
47 |  |  | Compose Message with Only Video | Phase - II | 2
48 |  |  | Compose Message with Text + Image | Phase - II | 2
49 |  |  | Compose Message with Video + Image | Phase - II | 4
50 |  |  | Choose Template | Completed | 2 | 2024-01-18 | 2024-01-27
51 |  |  | Choose Group | Completed
52 |  |  | Choose Schedule Message time or Now Send | Completed
53 |  |  | Send Message | Completed
54 |  | Messages List | Show All Messages | Inprogress | 1 | 2024-01-18 | 2024-01-27
55 |  |  | Search Filters for Messages List | Phase - II | 3
56 |  |  | Export the Messages List | Phase - II
57 | Chat | Chat | Send / Receive Chat Messages | Phase - II | 6
58 | Admin Panel | Dashboard | Summary Report of No of Users with Graph | Phase - II | 24
59 |  |  | Summary Report of No of Groups with Graph | Phase - II
60 |  |  | Summary Report of No of Messages Sent with Graph | Phase - II
61 |  |  | Summary Report of No of Messages Received with Graph | Phase - II
62 |  |  | Summary Report of No of Revenue Earned with Graph | Phase - II
63 |  | User Creation | Get user details including Name, Email and Password | Completed | 4 | 2024-01-19
64 |  |  | Get OTP for validate the Mobile No | Pending
65 |  |  | Assign Plans | Pending
66 |  |  | Create User | Completed
67 |  | User List | Show All users with Plans | Pending | 1 | 2024-01-19
68 |  |  | Edit / Delete the User | Phase - II | 3
69 |  |  | Search Filters for User List | Phase - II
70 |  |  | Export the User List | Phase - II
71 |  | Plan Creation | New Plan Title | Pending | 4 | 2024-01-20
72 |  |  | Monthly / Annual Price | Pending
73 |  |  | No of Whatsapp and Groups created | Pending
74 |  |  | Create Plan | Pending
75 |  | Plan List | Show All Existing Plans | Pending | 2 | 2023-10-17
76 |  |  | Monthly / Annual Plans with Cost | Completed
77 |  |  | Add / Edit / Delete the Plans | Pending | 6 | 2024-01-22
78 |  |  | Search Filters for Plan List | Completed
79 |  |  | Export the Plan List | Completed
80 |  | Report Management | Details Report of No of Users | Phase - II | 2
81 |  |  | Details Report of No of Groups | Phase - II | 2
82 |  |  | Details Report of No of Messages Sent | Phase - II | 2
83 |  |  | Details Report of No of Messages Received | Phase - II | 2
84 |  |  | Details Report of No of Revenue Earned | Phase - II | 2
85 |  |  | Search Filters for All reports | Phase - II | 2
86 |  |  | Export the All reports | Phase - II | 1
87 | Testing | Internal Testing and Issue Fixing | Round 1 - Testing | Pending | 8 | 2024-01-23 | 2024-01-23
88 |  |  | Issue Fixing | Pending | 12 | 2024-01-23 | 2024-01-24
89 |  |  | Round 2 - Testing | Pending | 8 | 2024-01-24 | 2024-01-24
90 |  |  | Issue Fixing | Pending | 8 | 2024-01-24 | 2024-01-25
91 |  |  | Round 3 - Testing | Pending | 4 | 2024-01-25 | 2024-01-25
92 |  | User Acceptance Testing (UAT) and Issue Fixing | Round 1 - Testing | Phase - II | 8
93 |  |  | Issue Fixing | Phase - II | 12
94 |  |  | Round 2 - Testing | Phase - II | 8
95 |  |  | Issue Fixing | Phase - II | 8
96 |  |  | Round 3 - Testing | Phase - II | 4
Total : |  |  |  |  | 222
| Required Details | OTP API required |  |  |  | Phase I
|  | SMTP & EMail login details required |  |  |  | Phase II
|  | Razor Pay Payment & login details required (Staging Test / Live) |  |  |  | Inprogress Tasks
Completed Tasks

## Sheet4
S.No | Tasks | Sub Tasks | Priority Order | Time to complete | Assigned To | Development Status | Testing Status | Developer Comments | Expected Start Date | Actual Start Date | Remarks | Expected Complete Date | Actual Completed Date
1 | Add a textfield to enter group name in add members to existing group page |  |  | 30Mins | Madhu bala | Completed |  |  | 2023-11-06 | 2023-11-07 |  | 2023-11-07 | 2023-11-07
2 | Dashboard report |  |  | 30 Mins | Madhu bala | Completed |  |  | 2023-11-06 | 2023-11-07 |  | 2023-11-07
3 | Summary report |  |  | 1 hour | Madhu bala | Completed |  |  | 2023-11-06 | 2023-11-07 |  | 2023-11-07 | 2023-11-07
4 | Detailed report |  |  | 1 hour | Madhu bala | Completed |  |  | 2023-11-06 | 2023-11-07 |  | 2023-11-07 | 2023-11-07
5 | Group list API |  |  | 15 Mins | Shanthini | Completed |  |  | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | 2023-11-06
6 | Sender id list not showing |  |  | 15 Mins | Madhu bala | Completed |  |  | 2023-11-06
7 | Credits issue API |  |  |  | Shanthini | Hold |  | assuming it is not an issue, we should in create group
8 | Send messages to group api |  |  | 1hr | Shanthini |  |  |  | 2023-11-07 |  |  | 2023-11-07
9 | Check the limits before creating group and adding sender id in API |  |  | 1hr | Shanthini | Completed |  |  | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | 2023-11-06
10 | Approve plan page should not visible for user |  |  | 30Mins | Madhu bala | Completed
11 | Validations |  |  |  | Madhu bala | Completed
12 | Detailed report API |  |  |  | Shanthini | Completed |  |  | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | 2023-11-06
13 | Summary report API with date filter |  |  |  | Shanthini | Completed |  |  | 2023-11-06 | 2023-11-06 |  | 2023-11-06 | 2023-11-06
14 | Dashboard report API |  |  | 1hr | Shanthini | Completed |  |  | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-07
15 | Create group and add group members to group from frontend |  |  |  | Madhu bala | Completed |  |  | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-07
2023-09-11
1 | Dashboard issue in superadmin summary |  |  |  | Madhu bala
2 | Change password - put the visible icon |  |  |  | Madhu bala
3 | Signin using Mobile number issue | API
4 | Add sender id - mobile number validation issue (accept dot, allow to type 1234 ) |  |  |  | Madhu bala | Completed | Testing Completed |  | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10
5 | QR code scan issue | API |  |  | Madhu bala | In Completed |  |  | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10
6 | sender id list - when click the scan button not working on submit button in add sender id |  |  |  | Madhu bala
7 | profile image - change the error msg.(mb value) |  |  |  | Madhu bala | Completed | Testing Completed |  | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10
2023-10-11
8 | Disable the coutry code (add sender id ) |  |  |  | Madhu bala | Completed | Testing Completed |  | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10
9 | pdf generation issue |  |  |  | Madhu bala | In Completed
10 | pricing plans list issue (update new plans date) |  |  |  | Madhu bala
11 | pricing plans list - search issue (user name) |  |  |  | Madhu bala | In Completed
12 | bold the word in search(All list page) |  |  |  | Madhu bala | Completed | Testing Completed |  | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10
13 | Payment History list - payment status button same width |  |  |  | Madhu bala | Completed | Testing Completed |  | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10
14 | payment history list - add payment issue |  |  |  | Madhu bala | Completed | Testing Completed |  | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10
15 | Generate Contact issue | API
16 | Add group contact - Mobile number validation |  |  |  | Madhu bala | In Completed
17 | Group list - entry date error change | API |  |  | Madhu bala | In Completed
18 | Add contact group - Mobile number validation , remove group name required option in one box. |  |  |  | Madhu bala
19 | group list - status button same width |  |  |  | Madhu bala | Completed | Testing Completed |  | 2023-11-10 | 2023-11-10 |  | 2023-11-10 | 2023-11-10
20 | Add contact in group - failure error occured(group list) | API
21 | Summary report- date order change | API
2023-11-11
22 | When add a contact in group, sender id unlinked | API
23 | Mobile no mismatch button issue |  |  |  | Madhu bala
24 | Add contact group- remove the no contacts found error when click the page.
25 | Add contact page - mobile number and group name selection issue
26 | csv file generation issue in payment history list |  |  |  | Madhu bala | Completed |  |  | 2023-11-11 | 2023-11-11 |  | 2023-11-11 | 2023-11-11
After getting sender id limit exceed error again qr code api hitting
Whatsapp GROUP - Already Complete To change 2024 - January
1 | Group Craete on user plan based |  |  | 2 Hours | Madhu bala | Completed |  |  | 2024-01-12 | 2024-01-12 |  | 2024-01-12 | 2024-01-12
2 | check the code client old client using on WhatsApp web js |  |  | 2 hours | Madhu bala | Completed |  |  | 2024-01-25 | 2024-01-26 |  | 2024-01-25 | 2024-01-26
3 | Integrate the code an api |  |  | 2 hours | Madhu bala | Completed |  |  | 2024-01-25 | 2024-01-26 |  | 2024-01-25 | 2024-01-26
4 | Testing the compose api. |  |  | 2 hours | Madhu bala | Completed |  |  | 2024-01-25 | 2024-01-26 |  | 2024-01-25 | 2024-01-26
5 | Bold mesasge send and url send on api & Testing |  |  | 2 hours | Madhu bala | Completed |  |  | 2024-01-25 | 2024-01-26 |  | 2024-01-25 | 2024-01-26